## TestCase
Product Name |  | Chaldal | TC Start Date | 2023-05-15 | TC Execution Start Date | 2023-05-18 |  |  |  |  | TEST CASE
Module Name |  | Register & Login | TC End Date | 2023-05-17 | TC Execution End Date | 2023-05-19 |  |  |  |  | PASS | 29
Epic |  |  | Test Case Developed By | Manik Hossain | Browser (tested) | Yes |  |  |  |  | FAIL | 5
Developer Name(TL) |  |  | Test Case Reviewed By |  | Performance (tested) | Yes |  |  |  |  | Not Executed | 0
Test Executed by | [10 empty] | Out of Scope | 0
[11 empty] | TOTAL | 34
#SL | Module | Type of Testing | Features | Test Cases Description | Test Data | Test Steps | Exepected Result | Actual Result | Bug Screen Shot | Dev Comments | Final Status | Remarks
TC-001 |  | Browser compatibility testing |  | Verify the site is compatible with different browsers | Chrome, Firefox, edge, interner explorer | Navigate to the URL- https://chaldal.com/ | Should be run in every browser | As expected |  |  | Passed
TC-002 | Register/Login | UI testing | Register/login | Verify all gramatical and spelling mistakes | N/A | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner | A pop up window appears and should not contain any gramatical and sppelling mistakes | As expected |  |  | Passed
TC-003 |  |  |  | Verify allignment of all field | N/A | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner | All field should be present in correct order | As expected |  |  | Passed
TC-004 |  |  |  | Verify font, text color | N/A | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner | Should be present as per requirement | As expected |  |  | Passed
TC-005 |  |  |  | Verify red cancel button is present in top-right corner | N/A | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner | Should be present as per requirement | As expected |  |  | Passed
TC-006 |  |  |  | Verify Facebook, Email, Mobile number are present for SignU or Login | N/A | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner | Should be present as per requirement | As expected |  |  | Passed
TC-007 |  |  |  | Verify Login with Email button is visible in login page | N/A | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner 3. Enter valid Phone number 4. Click on SIGN Up/ LOGIN button | Should be visible | As expected |  |  | Passed
TC-008 |  |  |  | Verify by clicking on SIGN UP/LOGIN button for blank input | N/A | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner 3. Click on SIGN Up/ LOGIN button | Should not go for next steps and show a validation message to enter a valid phone number | As expected |  |  | Passed
TC-009 |  |  |  | Verify county flag and code is visible correctly when I switch one to anoter | N/A | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner 3. Click on flag and select country name | Should display correct country flag and mobile number's country code | Not found properly | Click Me |  | Failed
TC-010 |  |  |  | Verify phone number example is displayed and field underline color is tomatoo when I click on Mobile Phone number field | N/A | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner 3. Click on Mobile Phone Number field | Should display 'e.g. +8801672955886' and color should be tomatoo | As expected |  |  | Passed
TC-011 |  |  |  | Verify phone number example is displayed correctly accourding to country | N/A | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner 3. Click on flag and select country name 4. Click on mobile number field | Should display correct mobile number example accourding to country code | Not found properly | Click Me |  | Failed
TC-012 |  |  |  | Verify phone number example color turn into tomatoo when I clik on Signup/login button | N/A | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner 3. Click on mobile number field 4. Click on Signup/Login button | Should turn into tomatoo color | As expected |  |  | Passed
TC-013 |  | Functional Testing |  | Verify Mobile number field with some invalid pattern | aaaaaaaaaaa,0111111iiii, 01!!!!!!!!!,013111 1111, ###########, , | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner 3. Enter Phone number 4. Click on SIGN Up/ LOGIN button | Should not go for next steps and show a validation message to enter a valid phone number | As expected |  |  | Passed
TC-014 |  |  |  | Verify Mobile number field with Bangladeshi Unauthorized serial number | 01034256758 01234256758 | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner 3. Enter Phone number 4. Click on SIGN Up/ LOGIN button | Should not go for next steps and show a validation message to enter a valid phone number | As expected |  |  | Passed
TC-015 |  |  |  | Verify Mobile number field with digit less than 11 and greater than 11 for bangladesh | 015215036298, 0152150362 | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner 3. Enter Phone number 4. Click on SIGN Up/ LOGIN button | Shouldnot go for next steps and show a validation message to enter a valid phone number | As expected |  |  | Passed
TC-016 |  |  |  | Verify Mobile number field without starting 01 | 56521503628 | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner 3. Enter Phone number 4. Click on SIGN Up/ LOGIN button | Shouldnot go for next steps and show a validation message to enter a valid phone number | As expected |  |  | Passed
TC-017 |  |  |  | Verify Mobile number field with a blank space between numbers | 01521503 29 | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner 3. Enter Phone number 4. Click on SIGN Up/ LOGIN button | Should not go for next steps and show a validation message to enter a valid phone number | As expected |  |  | Passed
TC-018 |  |  |  | Verify Mobile number field with a valid number | 1521503629 | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner 3. Enter Phone number 4. Click on SIGN Up/ LOGIN button | Should Navigate to Verification page for PIN | As expected |  |  | Passed
TC-019 |  |  |  | Verify 4 digi one time pin is sent to requested number | N/A | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner 3. Enter Phone number 4. Click on SIGN Up/ LOGIN button 5. Check your mobile message | Should Find a PIN | As expected |  |  | Passed
TC-020 |  |  |  | Verify entering invalid 4 digi one time PIN in PIN field | 1234, ####, xxxx | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner 3. Enter Phone number 4. Click on SIGN Up/ LOGIN button 5. Enter invalid PIN | Should not be register and show a validation message to enter correct PIN/OTP | As expected |  |  | Passed
TC-021 |  |  |  | Verify entering valid 4 digi one time PIN in PIN field after 3 min | valid pin | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner 3. Enter Phone number 4. Click on SIGN Up/ LOGIN button 5. Enter valid PIN after 3 min 6. Click on enter | Should not be register and navigate to Login page | As expected |  |  | Passed
TC-022 |  |  |  | Verify entering valid 4 digi one time PIN in PIN field within 3 min | valid pin | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner 3. Enter Phone number 4. Click on SIGN Up/ LOGIN button 5. Enter valid PIN within3 min 6. Click on enter | Should Register Successfully | As expected |  |  | Passed
TC-023 |  |  |  | Verify Request Pin Again button visibility | N/A | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner 3. Enter valid Phone number 4. Click on SIGN Up/ LOGIN button | Should be visible and clickable after 20 sec | As expected |  |  | Passed
TC-024 |  |  |  | Verify Request Pin Again button functionality | N/A | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner 3. Enter valid Phone number 4. Click on SIGN Up/ LOGIN button 5. Click on Request pin Again button agter 20 sec 6. Check requested mobile phone message | Should send a new PIN | As expected |  |  | Passed
TC-025 |  |  |  | Verify Requestes mobile number is visible in login page | 1521503629 | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner 3. Click login With Email button 4. enter email and password | Should Not be register and visible a validition message | As expected |  |  | Passed
TC-026 |  |  |  | Verify email with some invalid email format | testgmail.com test@gmailcom @gmail.com | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner 3. Click login with Email 4. Enter email 5. 5. Enter password 6. Click on LOGIN button | Should not be register and show an invalid email message | As expected |  |  | Passed
TC-027 |  |  |  | Verify email without valid domain | test@xyz.com | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner 3. Click login with Email 4. Enter email 5. 5. Enter password 6. Click on LOGIN button | Should not be register and show an invalid email message | As expected |  |  | Passed
TC-028 |  |  |  | Verify email field with tempmail | kopop94497@goflipa.com test@gmail.com | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner 3. Click login with Email 4. Enter email 5. 5. Enter password 6. Click on LOGIN button | Should not be register and show an invalid email message | As expected |  |  | Passed
TC-029 |  |  |  | Verify with valid email address | manikorj7@gmail.com Asdf12#456 | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner 3. Click login with Email 4. Enter email 5. 5. Enter password 6. Click on LOGIN button | Should Register and login Successfully | Showing an incorrect email or password message error | Click me |  | Failed
TC-030 |  |  |  | Verify Forgot password button functionality | N/A | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner 3. Click login with Email 4. Click on Forgot Password | Should navitgate to forgot password page | As expected |  |  | Passed
TC-031 |  |  |  | Verify Forgot password page email fucntionality | manikorj7@gmail.com | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner 3. Click login with Email 4. Click on Forgot Password 5. Enter email 6. Click on submit | Should display a message like 'A link has bneen sent to your email'. And find a link in email | No link sent to that email | Click me |  | Failed
TC-032 |  |  |  | Verify login with facebook | N/A | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner 3. Click login with facebook | Should login successfully | No response found | Click Me |  | Failed
TC-033 |  |  |  | Varify Facebook login button functionality when hover on it | N/A | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner 3. Hover on facebook | Button Colour displayed blue | As expected |  |  | Passed
|  |  |  | Verify cancle(x) icon | N/A | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner 3. Click on Cancel(x) icon | Should close login pop-up page | As expected |  |  | Passed
Click Here
Click Here

## Report
Test Case Report
Project Name - | Chaldal
Module Name - | Register/Login |  |  |  |  | Total No. | Status | Result :
Test Case Version | - |  |  |  |  | 29 | PASS
Written By | Manik Hossain |  |  |  |  | 5 | FAIL
Executed By | Manik Hossain |  |  |  |  | 0 | Not Executed | New Features | Testing Scope | Testing Environment :
Reviewed By | - |  |  |  |  | 0 | Out of Scope |  |  | Test Environment | Chrome, Firefox, Edge, Internet Explorer
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 29 | 5 | 0 | 0 | 34
Grand Total | 29 | 5 | 0 | 0 | 34
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting
# SL 009 | # SL 011 | # SL 029 | # SL 031
Issue: Wrong Country flag and code display | Issue: Example phone number isn't display correctly | Issue: Login fail through valid emal and password | Issue: Forgot password email verification fail
Expected : Should display correct country flag and mobile number's country code | Expected : Should display correct mobile number example accourding to country code | Expected : Should register and login | Expected : Should display a message like 'A link has bneen sent to your email'. And find a link in email
Actual: Not found properly | Actual: Not found properly | Actual: Showing an incorrect email or password message error | Actual: No link sent to that email
Test Steps: | Test Steps: | Test Steps: | Test Steps:
1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner 3. Click on flag and select country name | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner 3. Click on flag and select country name 4. Click on mobile number field | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner 3. Click login with Email 4. Enter email 5. Enter password 6. Click on LOGIN button | 1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner 3. Click login with Email 4. Click on Forgot Password 5. Enter email 6. Click on submit
Env: Production | Env: Production | Env: Production | Env: Production
Module: Register | Module: Register | Module: login | Module: login
Priority/Severity: low | Priority/Severity: Low | Priority/Severity: high | Priority/Severity: medium
Screenshot: Wrong Country flag and code display | Screenshot: Example phone number display issue | Screenshot: Login fail through email | Screenshot: No link sent to email
Responsible QA: Manik Hossain | Responsible QA: Manik Hossain | Responsible QA: Manik Hossain | Responsible QA: Manik Hossain
Bug Reporting
# SL 032
Issue: Login through facebook fail
Expected : Should login successfully
Actual: No response found
Test Steps:
1. Navigate to the URL- https://chaldal.com/ 2. Click on Sign in from top-right corner 3. Click login with facebook
Env: Production
Module: Login
Priority/Severity: medium
Screenshot: Login through Facebook fail
Responsible QA: Manik Hossain

## Test Metrics
Test Metrics |  |  |  | PASS | 29
|  |  |  | FAIL | 5
#SL | Metrics | Description | Result (%) | Not Executed | 0
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | 100 | Out of Scope | 0
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | 0 | TOTAL | 34
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | 85.2941
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | 14.7059
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A