## TestCase
Product Name |  | Walton Eplaza | TC Start Date | 2023-05-05 | TC Execution Start Date | 2023-05-07 |  |  |  |  | TEST CASE
Module Name |  | Register & Login | TC End Date | 2023-05-06 | TC Execution End Date | 2023-05-08 |  |  |  |  | PASS | 66
Epic |  |  | Test Case Developed By | Manik Hossain | Browser (tested) | Yes |  |  |  |  | FAIL | 12
Developer Name(TL) |  |  | Test Case Reviewed By |  | Performance (tested) | Yes |  |  |  |  | Not Executed | 0
Test Executed by | [10 empty] | Out of Scope | 0
[11 empty] | TOTAL | 78
#SL | Module | Type of Testing | Features | Test Cases Description | Test Data | Test Steps | Exepected Result | Actual Result | Bug Screen Shot | Dev Comments | Final Status | Remarks
TC-001 |  | Browser compatibility testing |  | Verify the site is compatible with different browsers | Chrome, Firefox, edge, interner explorer | Navigate to the URL- https://eplaza.waltonbd.com/ | Should be run in every browser | As expected |  |  | Passed
TC-002 | Register | UI testing | Register | Verify all gramatical and spelling mistakes | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register | Should not contain any gramatical and spelling mistakes | Not found properly | Click Here |  | Failed
TC-003 |  |  |  | Verify allignment of all field | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register | All field should be present in correct order | As expected |  |  | Passed
TC-004 |  |  |  | Verify font, text color | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register | Should be present as per requirement | As expected |  |  | Passed
TC-005 |  |  |  | Verify red asterist is present in mandatory fiels | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register | Should be present as per requirement | As expected |  |  | Passed
TC-006 |  |  |  | Verify all fields related to registration are present | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register | Should be present as per requirement | As expected |  |  | Passed
TC-007 |  |  |  | Verify password requirements are visible | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register | Should be present as per requirement | As expected |  |  | Passed
TC-008 |  |  |  | Verify an eye icon addedd on the password and confirm password field | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register | Should be present | As expected |  |  | Passed
TC-009 |  |  |  | Verify a check box is present before Continue button | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register | Should be present | As expected |  |  | Passed
TC-010 |  |  |  | Checking 'Privacy Policy' checkbox is not enabled by default | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register | Should be present unchecked | As expected |  |  | Passed
TC-011 |  | Functional Testing |  | Verify by clicking on the continue button for blank input | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Click on Continue | Should not be register and show a validation message like 'You must agree to Privacy Policy!' | As expected |  |  | Passed
TC-012 |  |  |  | Verify by clicking on check box and the continue button for blank input | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Click on Check box 5. Click on Continue | Should not be register and show error message for mandatory fields | As expected |  |  | Passed
TC-013 |  |  |  | Checking alert message for all mandatory fields | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Click on Check box 5. Click on Continue | Should pop an error message | Not found as per expectation |  |  | Passed
TC-014 |  |  |  | Verify First Name and Last Name with charactter less value than minimum and greater value than maximum | fname:a, lname:b fname: 34 times a , lname: 34 times b | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter First Name, Last Name 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should not be register and show warning message for First Name and Last Name can contain character between 2 and 32 | As expected |  |  | Passed
TC-015 |  |  |  | Verify First Name and Last Name field with insensitive characters | fname:aaaa, lname:bbbb | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter First Name, Last Name 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should not be register and show an error message | Registration successfully | Click Here |  | Failed
TC-016 |  |  |  | Verify First Name and Last Name field with special character only | fname:@@##, lname:@#&! | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter First Name, Last Name 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should not be register and show an error message | Registration successfully | Click Here |  | Failed
TC-017 |  |  |  | Verify First Name and Last Name field with numarical number only | fname:12345, lname: 65432 | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter First Name, Last Name 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should not be register and show an error message | Registration successfully | Click Here |  | Failed
TC-018 |  |  |  | Verify First Name and Last Name field with blank space before name | fname: Manik, lname: Hossain | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter First Name, Last Name 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should not be register and show an error message | Registration successfully | Click Here |  | Failed
TC-019 |  |  |  | Verify First Name and Last Name field with blank space after name | fname: Manik , lname: Hossain , | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter First Name, Last Name 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should not be register and show an error message | Registration successfully | Click Here |  | Failed
TC-020 |  |  |  | Verify First Name and Last Name field name with numbers | fname: Manik675, lname:Hossain54, fname: Manik675, lname: Hossain54, | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter First Name, Last Name 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should not be register and show an error message | Registration successfully | Click Here |  | Failed
TC-021 |  |  |  | Verify email with some invalid email format | testgmail.com test@gmailcom @gmail.com | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter email address 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should not be register and show an invalid email message | As expected |  |  | Passed
TC-022 |  |  |  | Verify email without valid domain | test@xxxx.com | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter email address 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should not be register and show an invalid email message | Registration successfully | Click Here |  | Failed
TC-023 |  |  |  | Verify with valid email address | manik.hossain_27@outlook.com | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter email address 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should Register Successfully | Registration successfully |  |  | Passed
TC-024 |  |  |  | Verify with valid but existing email address | manik.hossain_27@outlook.com | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter already existing email address 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should not be register and show a validation message like 'E-Mail Address is already registered!' | As expected |  |  | Passed
TC-025 |  |  |  | Verify email with Uppercase Letter | KinamNiasSoh@gmail.com | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter an uppercase letter email 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should Register Successfully | As expected |  |  | Passed
TC-026 |  |  |  | Verify Mobile number field with some invalid pattern | aaaaaaaaaaa,0111111iiii, 01!!!!!!!!!,013111 1111, ###########, , | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter Mobile Number 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should not be register and show a warning message like 'Please enter 11 digits valid mobile number!' | As expected |  |  | Passed
TC-027 |  |  |  | Verify Mobile number field with digit less than 11 and greater than 11 | 015215036298, 0152150362 | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter Mobile Number 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should not be register and show a validation message like 'Please enter 11 digits valid mobile number!' | As expected |  |  | Passed
TC-028 |  |  |  | Verify Mobile number field with not use operator codes | 01055555555, 01255555555 | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter Mobile Number 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should not be register and show a validation message like 'Please enter correct mobile numbers' | Registration successfully | Click Here |  | Failed
TC-029 |  |  |  | Verify Mobile number field without starting 01 | 56521503628 | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter Mobile Number 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should not be register and show a warning message like 'Please enter 11 digits valid mobile number!' | As expected |  |  | Passed
TC-030 |  |  |  | Verify Mobile number field with a blank space between numbers | 01521503 29 | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter Mobile Number 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should not be register and show a validation message like 'Please enter 11 digits valid mobile number!' | As expected |  |  | Passed
TC-031 |  |  |  | Verify Mobile number field with a valid number | 15215036298 | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter Mobile Number 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should Register Successfully | As expected |  |  | Passed
TC-032 |  |  |  | Verify minimum and maximum lengrh of address field | ab, characters number>128 | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter Address 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should not be register and show a validation message like 'Address must be between 3 and 128 characters!' | As expected |  |  | Passed
TC-033 |  |  |  | Verify address field as blank address | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Don't write in Address field 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should not be register and show a validation message like 'Address must be between 3 and 128 characters!' | As expected |  |  | Passed
TC-034 |  |  |  | Verify wheather the user can enter a combination of alphabet, numeric, special characters | 22# Narindha Rd. Dhaka | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter Address 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should Register Successfully | As expected |  |  | Passed
TC-035 |  |  |  | Verify address field with blank space only | [ ] | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter Address 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should not be register and notify a message for enter valid address | Registration successfully | Click Here |  | Failed
TC-036 |  |  |  | Verify password and confirm password field as blank |  | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Don't enter Password 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should not be register and notify a message for enter valid password as requirements | As expected |  |  | Passed
TC-037 |  |  |  | Verify password and confirm password field with numarical number only | 12345678 | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter Password and Confirm Password 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should not be register and notify a message for enter valid password as requirements | As expected |  |  | Passed
TC-038 |  |  |  | Verify password and confirm password field with alphabets only | abcdefgh | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter Password and Confirm Password 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should not be register and notify a message for enter valid password as requirements | As expected |  |  | Passed
TC-039 |  |  |  | Verify password and confirm password field with special characters only | %@#$%^&*! | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter Password and Confirm Password 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should not be register and notify a message for enter valid password as requirements | As expected |  |  | Passed
TC-040 |  |  |  | Verify password and confirm password field with Uppercase or Lowercase alphabets only | ABCDEFGH abcdefgh | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter Password and Confirm Password 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should not be register and notify a message for enter valid password as requirements | As expected |  |  | Passed
TC-041 |  |  |  | Verify password & confirm password field with the combination of numaric,alphabets,special charracter | ABC123#&* abc123##** | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter Password and Confirm Password 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should not be register and notify a message for enter valid password as requirements | As expected |  |  | Passed
TC-042 |  |  |  | Verify password & confirm password field with the combination of uppercase & lowercase alphabets, numbes, numaric,special charracter | ABcd12@# Abcd 12# | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter Password and Confirm Password 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should Register Successfully | As expected |  |  | Passed
TC-043 |  |  |  | Verify mismatched in password & confirm password field with valid sequence of password | Password: ABcd12@# Confirm Password: Abcd 12# | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter Password and Confirm Password 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should not be register and notify a message like 'Password confirmation does not match password!' | As expected |  |  | Passed
TC-044 |  |  |  | Verify strength meter bar for weak password | Aabbcc1 | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter Password and Confirm Password 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should show a weak meter bar | As expected |  |  | Passed
TC-045 |  |  |  | Verify strength meter bar for medium password | Aaa11# | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter Password and Confirm Password 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should show a midium meter bar | As expected |  |  | Passed
TC-046 |  |  |  | Verify strength meter bar for strong password | ABcd12## | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter Password and Confirm Password 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should show a strong meter bar | As expected |  |  | Passed
TC-047 |  |  |  | Check if the password is visible or encrypted | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter Password and Confirm Password 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should be visible | As expected |  |  | Passed
TC-048 |  |  |  | Check the min char limit for the password fields | Ab1@ | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter Password and Confirm Password 5. Enter other valid field 6. Click on check box 7. Click on Continue | Should not be register and show a validation message like 'Password too short' | As expected |  |  | Passed
TC-049 |  |  |  | Verify unchecked check box | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter all valid field 5. Don't click on check box 6. Click on Continue | Should not be register and show a validation message like 'You must agree to Privacy Policy!' | As expected |  |  | Passed
TC-050 |  |  |  | Verify Privacy Policy is clickable | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Click on Privacy Policy | Should be clickable and navigate to Privacy Plicy page | As expected |  |  | Passed
TC-051 |  |  |  | Verify Privacy Policy open in new tab | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Click on Privacy Policy | Should be visible in new tab | Visible in current tab | Click Here |  | Failed
TC-052 |  |  |  | Verify Continue button after entering all valid data | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter all valid field 5. Click on check box 6. Click on Continue | Should Register Successfully | As expected |  |  | Passed
TC-053 |  |  |  | Verify Confirmation message is sent to the registered email | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter all valid field 5. Click on check box 6. Click on Continue | Should Sent a message to the registered email successfully | As expected |  |  | Passed
TC-054 |  | Usability Testing |  | Verify Keyboard enter button functionality | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter all field witf valid data 5. Click on check box 6. Press keyboard enter button | Should do similar task as Continue button | As expected |  |  | Passed
TC-055 |  |  |  | Verify Keyboard tab button functionality | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Press Keyboard tab button | Should switch one field to following field | As expected |  |  | Passed
TC-056 |  |  |  | Verify copy-paste functionality in every input field | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Enter any field with valid data and copy it 4. Paste it to another field | Should copy-paste in field | As expected |  |  | Passed
TC-057 | Login | UI testing | Login | Verify all gramatical and spelling mistakes | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Login | Should not contain any gramatical and sppelling mistakes | Not found properly | Click Here |  | Failed
TC-058 |  |  |  | Verify allignment of all field | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Login | All field should be present in correct order | As expected |  |  | Passed
TC-059 |  |  |  | Verify font, text color | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Login | Should be present as per requirement | As expected |  |  | Passed
TC-060 |  |  |  | Verify all fields related to Login are present | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Login | Should be present as per requirement | As expected |  |  | Passed
TC-061 |  |  |  | Verify 'Forgotten Password' is visible | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Login | Should be visible as per requirement | As expected |  |  | Passed
TC-062 |  |  |  | Verify 'Don't have an account? Register for a new account' and a Continue button is visible | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Login | Should be visible as per requirement | As expected |  |  | Passed
TC-063 |  | Functional Testing |  | Verify login page for both email and password field blank and Login button is clicked | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Login from navbar 4. Click on Login Button | Should not be Login and show a warning message like 'not match for E-Mail Address and/or Password | As expected |  |  | Passed
TC-064 |  |  |  | Verify login page for both email and password field with invalid data and Login button is clicked | email:test32@gmail.com Password: Asqw1@k# | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. enter invalid email and invalid password 4. Click on Login Button | Should not be Login and show a warning message like 'not match for E-Mail Address and/or Password | As expected |  |  | Passed
TC-065 |  |  |  | Verify login page for valid email and invalid password and Login button is clicked | email:Kinam@gmail.com Password: Asqw1@k# | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. enter valid email and invalid password 4. Click on Login Button | Should not be Login and show a warning message like 'not match for E-Mail Address and/or Password | As expected |  |  | Passed
TC-066 |  |  |  | Verify login page for invalid email and valid password and Login button is clicked | email:test32@gmail.com Password: Abcd123@ | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. enter invalid email and valid password 4. Click on Login Button | Should not be Login and show a warning message like 'not match for E-Mail Address and/or Password | As expected |  |  | Passed
TC-067 |  |  |  | Verify login page for both valid email and valid password and Login button is clicked | email:Kinam@gmail.com Password: Abcd123@ | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. enter valid email and valid password 4. Click on Login Button | Should Login Successfully and navigate to user home page | As expected |  |  | Passed
TC-068 |  |  |  | Verify 'Forgotten Password' functionality | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Forgotten Password | Should Navigate to reset password page to query about email | As expected |  |  | Passed
TC-069 |  |  |  | Verify Continue button functionality if I don't have an account | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Forgotten Password | Should navigate to register page | As expected |  |  | Passed
TC-070 | Header |  | Header | Verify all gramatical and spelling mistakes | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ | Should not contain any gramatical and sppelling mistakes | As expected |  |  | Passed
TC-071 |  |  |  | Verify allignment of all field | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ | All field should be present in correct order | As expected |  |  | Passed
TC-072 |  |  |  | Verify font, text color | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ | Should be present as per requirement | As expected |  |  | Passed
TC-073 |  |  |  | Verify icons are attatched with appropiate list name | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ | Should be present as per requirement | As expected |  |  | Passed
TC-074 |  |  |  | Verify list color when hover on it | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ | Color should change when hover | As expected |  |  | Passed
TC-075 |  |  |  | Verify list are clickable | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ | List should be clickable | As expected |  |  | Passed
TC-076 |  |  |  | Verify walton logo is clickable | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ | Logo is clickable and navigare to home page | As expected |  |  | Passed
TC-077 |  |  |  | Verify Search is written in serchbox | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ | Search should be written in serchbox | As expected |  |  | Passed
TC-078 |  |  |  | Verity plaza list is open in new tab | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on Plaza List | Plaza list open in new tab | As expected |  |  | Passed
TC-079 |  |  |  |  | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/
TC-080 |  |  |  |  | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/
TC-081 |  |  |  |  | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/
TC-082 |  |  |  |  | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/
TC-083 |  |  |  |  | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/
TC-084 |  |  |  |  | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/
TC-085 |  |  |  |  | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/
TC-086 |  |  |  |  | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/
[5 empty] | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/
[5 empty] | N/A | 1. Navigate to the URL- https://eplaza.waltonbd.com/
|  |  | Improvement Scopes | Register & Login form can be placed in center
A link can be added in register page to navigate to login page for already registrated user
Can add remember me checkbox in login page

## Report
Test Case Report
Project Name - | Walton Eplaza
Module Name - | Register/Login |  |  |  |  | Total No. | Status | Result :
Test Case Version | [5 empty] | 66 | PASS
Written By | Manik Hossain |  |  |  |  | 12 | FAIL
Executed By | Manik Hossain |  |  |  |  | 0 | Not Executed | New Features | Testing Scope | Testing Environment :
Reviewed By | - |  |  |  |  | 0 | Out of Scope |  |  | Test Environment | Chrome, Firefox, Edge, Internet Explorer
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 66 | 12 | 0 | 0 | 78
Grand Total | 66 | 12 | 0 | 0 | 78
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting
# SL 002 | # SL 015 | # SL 016 | # SL 017
Issue: Gramatical and spelling mistakes | Issue: First Name and Last Name field with insensitive characters | Issue: First Name and Last Name field with special characters | Issue: First Name and Last Name field with special characters
Expected : Should not contain any gramatical and spelling mistakes | Expected : Should not be register and show an error message | Expected : Should not be register and show an error message | Expected : Should not be register and show an error message
Actual: Spelling mistakes found | Actual: Registration Successfully | Actual: Registration Successfully | Actual: Registration Successfully
Test Steps: | Test Steps: | Test Steps: | Test Steps:
1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter First Name, Last Name 5. Enter other valid field 6. Click on check box 7. Click on Continue | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter First Name, Last Name 5. Enter other valid field 6. Click on check box 7. Click on Continue | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter First Name, Last Name 5. Enter other valid field 6. Click on check box 7. Click on Continue
Env: Production | Env: Production | Env: Production | Env: Production
Module: Register | Module: Register | Module: Register | Module: Register
Priority/Severity: low | Priority/Severity: Low | Priority/Severity: Low | Priority/Severity: Low
Screenshot: Gramatical and Spelling mistakes | Screenshot: Name with Insensitive character | Screenshot: Name with Insensitive character | Screenshot: Name with special character
Responsible QA: Manik Hossain | Responsible QA: Manik Hossain | Responsible QA: Manik Hossain | Responsible QA: Manik Hossain
Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting
# SL 018 | # SL 019 | # SL 020 | # SL 022
Issue: First Name and Last Name field with Numarical numbers | Issue: First Name and Last Name field with blank space after name | Issue: First Name and Last Name field name with numbers | Issue: Registrated with invalid domain of email
Expected : Should not be register and show an error message | Expected : Should not be register and show an error message | Expected : Should not be register and show an error message | Expected : Should not be register and show an error message
Actual: Registration Successfully | Actual: Registration Successfully | Actual: Registration Successfully | Actual: Registration Successfully
Test Steps: | Test Steps: | Test Steps: | Test Steps:
1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter First Name, Last Name 5. Enter other valid field 6. Click on check box 7. Click on Continue | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter First Name, Last Name 5. Enter other valid field 6. Click on check box 7. Click on Continue | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter First Name, Last Name 5. Enter other valid field 6. Click on check box 7. Click on Continue | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter email address 5. Enter other valid field 6. Click on check box 7. Click on Continue
Env: Production | Env: Production | Env: Production | Env: Production
Module: Register | Module: Register | Module: Register | Module: Register
Priority/Severity: Low | Priority/Severity: Low | Priority/Severity: Low | Priority/Severity: High
Screenshot: Name with numaric numbers | Screenshot: Name contain blank space | Screenshot: Name with numbers | Screenshot: Name with Insensitive character
Responsible QA: Manik Hossain | Responsible QA: Manik Hossain | Responsible QA: Manik Hossain | Responsible QA: Manik Hossain
Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting
# SL 028 | # SL 034 | # SL 050 | # SL 056
Issue: Verify Mobile number field with not use operator codes | Issue: Address field accepted space only | Issue: Privacy Policy open in existing tab | Issue: Gramatical and spelling mistakes
Expected : Should not be register and show an error message | Expected : Should not be register and show an error message | Expected : Should be visible in new tab | Expected : Should not contain any gramatical and spelling mistakes
Actual: Registration Successfully | Actual: Registration Successfully | Actual: Visible in current tab | Actual: Spelling mistakes found
Test Steps: | Test Steps: | Test Steps: | Test Steps:
1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter Mobile number field with not use operator codes 5. Enter other valid field 6. Click on check box 7. Click on Continue | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Enter Address field with blank space 5. Enter other valid field 6. Click on check box 7. Click on Continue | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Register 4. Click on Privacy Policy | 1. Navigate to the URL- https://eplaza.waltonbd.com/ 2. Click on My Account 3. Click on Login
Env: Production | Env: Production | Env: Production | Env: Production
Module: Register | Module: Register | Module: Register | Module: Sign in
Priority/Severity: Midium | Priority/Severity: Low | Priority/Severity: Low | Priority/Severity: low
Screenshot: Address field accepted only space | Screenshot: Address field accepted only space | Screenshot: Privicy policy open in new tab | Screenshot: Gramatical and Spelling mistakes
Responsible QA: Manik Hossain | Responsible QA: Manik Hossain | Responsible QA: Manik Hossain | Responsible QA: Manik Hossain

## Mind Maps
To See in PDF Version | Click Me

## Test Metrics
Test Metrics |  |  |  | PASS | 66
|  |  |  | FAIL | 12
#SL | Metrics | Description | Result (%) | Not Executed | 0
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | 100 | Out of Scope | 0
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | 0 | TOTAL | 78
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | 84.6154
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | 15.3846
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A